## Sheet1
Component / Feature | Status | Est. Effort (hrs) | Est. Date | Notes
Branch model + create/list API | ✅ Complete | 3 | Done | Includes DB + routes
Branch CRUD (update, delete) | To Do | 4 | TBD | Edit branch name; delete branch
Commit model + create/list API | ✅ Complete | 4 | Done | Core commit engine
Commit CRUD (update message, delete) | To Do | 4 | TBD | Edit commit message; delete commit
Rollback functionality | To Do | 3 | TBD | Git‑like rollback, needs testing
Commit bug fix (creation failure) | ✅ Complete | 2 | 2‑Apr | Needs debugging + frontend feedback
Tag model + create/query by commit | ✅ Complete | 3 | Done | Working via API
Tag CRUD (update name, delete) | To Do | 3 | TBD | Rename or remove tags
Search by commit tags | To Do |  | TBD
Tag display on frontend | ✅ Complete | 2 | 4‑Apr | Show tags on CommitCard
Branch switcher UI | ✅ Complete | 4 | Done | UX tested
Per‑branch commit log | ✅ Complete | 3 | Done | /branches/[id] page
Commit form UI | ✅ Complete | 2 | Done | Integrated with branch context
OpenAI Integration (via API key) | ✅ Working | 3 | Done | Chat‑to‑commit proofed
Browser extension for ChatGPT → ChatCommit | ✅ Working | 12 | 10‑Apr | Includes popup UI + background injection
Git‑like features (merge, timeline, diff) | 🛠️ To Do | 8 | 14‑Apr | Merge logic, backend APIs
Tag timeline/history view | 🛠️ To Do | 4 | 16‑Apr | Visual timeline per tag
User sign‑on (extension settings?) | To Do |  | TBD
Modify database to support accounts | To Do |  | TBD
Here are ten high‑impact channels you can use to promote ChatCommit, along with a brief description of each:
Product Hunt
Launch your app on Product Hunt to reach an audience of early adopters and makers.
🔗 https://www.producthunt.com/
Description: Showcase new features, gather feedback, and climb the daily leaderboard.
Indie Hackers
Share your journey and updates with a community of bootstrappers.
🔗 https://www.indiehackers.com/
Description: Post a “Launch” thread, participate in discussions, and ask for feedback.
Hacker News
Submit a “Show HN: ChatCommit…” post to the Y Combinator community.
🔗 https://news.ycombinator.com/
Description: If your product resonates, it can drive significant traffic and interest.
Twitter
Tweet feature announcements, tutorials, and success stories.
🔗 https://twitter.com/
Description: Use hashtags like #Productivity, #DevTools, and #AI to increase visibility.
LinkedIn
Write an article about how ChatCommit streamlines ChatGPT version control.
🔗 https://www.linkedin.com/
Description: Share in relevant groups (e.g., “AI & Machine Learning,” “Software Development”).
Reddit – r/Productivity
Introduce ChatCommit to a productivity‑focused audience.
🔗 https://www.reddit.com/r/productivity/
Description: Highlight how it helps maintain conversation history and project notes.
Reddit – r/ArtificialIntelligence
Engage AI enthusiasts who use ChatGPT regularly.
🔗 https://www.reddit.com/r/artificial/
Description: Share use cases and ask for feedback on AI‑driven features.
Dev.to
Write a technical post about integrating ChatCommit into your workflow.
🔗 https://dev.to/
Description: Tag with #javascript, #nextjs, and #fastapi for targeted reach.
GitHub Discussions
Open a Discussion in your repo for “Showcase & Feedback.”
🔗 https://github.com/nrbessmer/ChatCommit/discussions
Description: Encourage users to share how they’re using the tool and suggest features.
Stack Overflow Chat Rooms
Join relevant chat rooms (e.g., “#javascript,” “#python”) and share your project link.
🔗 https://chat.stackoverflow.com/
Description: Engage in real‑time with developers, answer questions, and casually mention ChatCommit when relevant.