## Sheet1
Component / Feature | Status | Est. Effort (hrs) | Est. Date (EOD) | Notes
Branch model + create/list API | ✅ Complete | 3 | Done | Includes DB + routes
Commit model + create/list API | ✅ Complete | 4 | Done | Core commit engine
Rollback functionality | To Do | 3 | Needs to be testted | Git-like rollback
Commit bug fix (creation failure) | Complete | 2 | 2025-04-02 | Needs debugging + frontend feedback
Tag model + create/query by commit | ✅ Complete | 3 | Done | Working via API
Search by commit tags | To Do
Tag display on frontend | Complete | 2 | 2025-04-04 | Show tags on CommitCard
Branch switcher UI | ✅ Complete | 4 | Done | UX tested
Per-branch commit log | ✅ Complete | 3 | Done | /branch/[id] page
Commit form UI | ✅ Complete | 2 | Done | Integrated with branch context
OpenAI Integration (via API key) | ✅ Working | 3 | Done | Chat-to-commit proofed
Browser extension for ChatGPT -> ChatCommit | Working | 12 | 2025-04-10 | Includes popup UI + background injection
Git-like features (merge, timeline, diff) | 🛠️ To Do | 8 | 2025-04-14 | Merge logic, backend APIs
Tag timeline/history view | 🛠️ To Do | 4 | 2025-04-16 | Visual timeline per tag
User sign on? Or is that done through the settings in the extension? | To Do
Modify database to support accounts! | To Do
Docs (README, How-To, Architecture) | 🛠️ To Do | 6 | 2025-04-22 | Markdown docs on GitHub
Deployment (Fly.io/Render + DB setup) | 🛠️ To Do | 4 | 2025-04-24 | MVP deployment for feedback
Promotion (LinkedIn, Twitter, IndieHackers) | 🛠️ To Do | 4 | 2025-04-26 | Post launch