## Sheet1
Component / Feature | Status | Est. Effort (hrs) | Est. Date | Notes
Branch model + create/list API | ✅ Complete | 3 | Done | Includes DB + routes
Commit model + create/list API | ✅ Complete | 4 | Done | Core commit engine
Rollback functionality | To Do | 3 | TBD | Git‑like rollback, needs testing
Commit bug fix (creation failure) | ✅ Complete | 2 | 2‑Apr | Needs debugging + frontend feedback
Tag model + create/query by commit | ✅ Complete | 3 | Done | Working via API
Search by commit tags | To Do |  | TBD
Tag display on frontend | ✅ Complete | 2 | 4‑Apr | Show tags on CommitCard
Branch switcher UI | ✅ Complete | 4 | Done | UX tested
Per‑branch commit log | ✅ Complete | 3 | Done | /branches/[id] page
Commit form UI | ✅ Complete | 2 | Done | Integrated with branch context
OpenAI Integration (via API key) | ✅ Working | 3 | Done | Chat‑to‑commit proofed
Browser extension for ChatGPT → ChatCommit | ✅ Working | 12 | 10‑Apr | Includes popup UI + background injection
Git‑like features (merge, timeline, diff) | 🛠️ To Do | 8 | 14‑Apr | Merge logic, backend APIs
Tag timeline/history view | 🛠️ To Do | 4 | 16‑Apr | Visual timeline per tag
User sign‑on (extension settings?) | To Do |  | TBD
Modify database to support accounts | To Do |  | TBD
Docs (README, How‑To, Architecture) | 🛠️ To Do | 6 | 22‑Apr | Markdown docs on GitHub
Deployment (Fly.io/Render + DB setup) | 🛠️ To Do | 4 | 24‑Apr | MVP deployment for feedback
Promotion (LinkedIn, Twitter, IndieHackers) | 🛠️ To Do | 4 | 26‑Apr | Post launch